## Projects
Project Key | Requested Date | Process | Client | Speciality/Practice | Billing System | Systems Involved | SPOC | Host Platform | User Group Involved | Impact | Task Name | Frequency | Time Taken/Transaction | Transactions Produced | Hours Saved/Execution | FTEs Saved | Overall Cost Saved | Project Name | Version | Bot Nature | Developed Plaform | Kick-Off | Actual Live | Last Execution Date | Planned Days | Live Month | Developer | Feasibility | Project Status | Active Status | Remarks
2024_001 | 2024-09-16 | Accounts Receivable | Rume Medical Group |  | CollaborateMD | CollaborateMD | Sanjith Nair | Chrome/Browser | Users | Production | Claim Status | Daily | 0:05 | 30449 | 2537:25 | 317.1771 | 253741.6667 | Rume Medical Group Accounts Receivable - Claim Status | 1.0 | Unattended | UiPath | 2024-09-16 | 2024-09-19 | 2024-12-09 | 3 | 09-2024 | Arun Kumar S | Yes | Live | Inactive
2024_002 | 2024-10-20 | Accounts Receivable | Elevated Health Inc |  | CollaborateMD | CollaborateMD | Sanjith Nair | Chrome/Browser | Users | Production | Claim Status | Daily | 0:05 | 21899 | 1824:55 | 228.1146 | 182491.6667 | Elevated Health Inc Accounts Receivable - Claim Status | 1.0 | Unattended | UiPath | 2024-10-20 | 2024-10-20 | 2024-12-09 | 0 | 10-2024 | Arun Kumar S | Yes | Live | Inactive
2024_003 | 2024-10-07 | Accounts Receivable | Rume Medical Group |  | CollaborateMD | CollaborateMD | Sanjith Nair | Chrome/Browser | Users | Production | Appeal Letter | Daily | 0:06 | 97 | 9:42 | 1.2125 | 970 | Rume Medical Group Accounts Receivable - Appeal Letter | 1.0 | Unattended | VBA+Selenium | 2024-10-07 | 2024-10-28 | 2024-12-09 | 21 | 10-2024 | Arun Kumar S | Yes | Live | Inactive
2024_004 | 2024-10-07 | Accounts Receivable | Elevated Health Inc |  | CollaborateMD | CollaborateMD | Sanjith Nair | Chrome/Browser | Users | Production | Appeal Letter | Daily | 0:06 | 21703 | 2170:18 | 271.2875 | 217030 | Elevated Health Inc Accounts Receivable - Appeal Letter | 1.0 | Unattended | VBA+Selenium | 2024-10-07 | 2024-10-28 | 2024-12-09 | 21 | 10-2024 | Arun Kumar S | Yes | Live | Inactive
[15 empty] | 0:00 | 0 | 0 | - | [6 empty] | 0 | 01-1900